## Sheet1
Story | Priority | Cost est. | Source | Parking | Forecast | Hold | Blocked | To Do | WIP | Done | Date
Retrieve data from live URL
fetch(API) with React | 1 | 3 | Back-end | [6 empty] | x | 2018-10-24
jQuery AJAX with React | 1 | 2 | Back-end | [6 empty] | x | 2018-10-24
PHP with React | 1 | 2 | Back-end | [6 empty] | x | 2018-10-24
Global temperature viz
Custom chart theming | 3 | 3 | User | [6 empty] | x | 2018-10-26
Data structure (mock) | 1 | 1 | User | [6 empty] | x | 2018-10-26
NodeJS/Express with create-react-app (to fetch data from live URL) | 1 | 5 | Back-end | [6 empty] | x | 2018-11-02
Global CO2 emissions viz
Custom chart theming | 3 | 1 | User | [6 empty] | x | 2018-11-15
Fetch data live (FTP protocol) | 1 | 5 | User | [6 empty] | x | 2018-11-15
Global Carbon budget viz
Custom chart theming | 3 | 1 | User | [6 empty] | x | 2018-11-14
Fetch data from excel | 1 | 5 | Back-end | [6 empty] | x | 2018-11-14
Tips/solutions viz | 1 | 8 | User |  |  |  |  | x
About Page | 2 | 2 | User | [6 empty] | x | 2018-11-13
Articles Pages | 3 | 2 | User | [6 empty] | x | 2018-11-13
Learn Redux
Egghead series by Dan Abramov | 2 | 10 | Back-end | [6 empty] | x | 2018-11-03
Use React with Redux (1) | 2 | 5 | Back-end | [6 empty] | x | 2018-11-04
Use React with Redux (2) | 2 | 6 | Back-end | [6 empty] | x | 2018-11-04
Carousel component with Redux
Component with buttons | 3 | 1 | User | [6 empty] | x | 2018-11-07
Actions and reducers | 3 | 2 | User | [6 empty] | x | 2018-11-07
Connect() with store | 3 | 5 | User | [6 empty] | x | 2018-11-07
React route | 2 | 5 | User |  |  |  |  | x
SASS styling (pages) | 2 | 21 | User |  | x |  |  | x
!!! Items that are in forecast need to be broken down to smaller tasks