## Sheet1
Story | Priority | Cost est. | Source | Parking | Forecast | Hold | Blocked | To Do | WIP | Done | Date
Retrieve data from live URL | 1 | 7
fetch(API) with React | 1 | 3 | Back-end | [6 empty] | x | 2018-10-24
jQuery AJAX with React | 1 | 2 | Back-end | [6 empty] | x | 2018-10-24
PHP with React | 1 | 2 | Back-end | [6 empty] | x | 2018-10-24
Global temperature viz | 1 | 9
Custom chart theming | 3 | 3 | User | [6 empty] | x | 2018-10-26
Data structure (mock) | 1 | 1 | User | [6 empty] | x | 2018-10-26
NodeJS/Express with create-react-app (to fetch data from live URL) | 1 | 5 | Back-end | [6 empty] | x | 2018-11-02
Global CO2 emissions viz | 1 | 6
Custom chart theming | 3 | 1 | User | [6 empty] | x | 2018-11-15
Fetch data live (FTP protocol) | 1 | 5 | User | [6 empty] | x | 2018-11-15
Global Carbon budget viz | 1 | 6
Custom chart theming | 3 | 1 | User | [6 empty] | x | 2018-11-14
Fetch data from excel | 1 | 5 | Back-end | [6 empty] | x | 2018-11-14
Testing on different devices & Record bugs (front and back end) | 1 | 8 | User | [6 empty] | x | 2018-11-30
About Page | 2 | 2 | User | [6 empty] | x | 2018-11-13
Articles Pages | 3 | 2 | User | [6 empty] | x | 2018-11-13
Learn Redux | 2 | 21
Egghead series by Dan Abramov | 2 | 10 | Back-end | [6 empty] | x | 2018-11-03
Use React with Redux (1) | 2 | 5 | Back-end | [6 empty] | x | 2018-11-04
Use React with Redux (2) | 2 | 6 | Back-end | [6 empty] | x | 2018-11-04
Carousel component with Redux | 3 | 8
Component with buttons | 3 | 1 | User | [6 empty] | x | 2018-11-07
Actions and reducers | 3 | 2 | User | [6 empty] | x | 2018-11-07
Connect() with store | 3 | 5 | User | [6 empty] | x | 2018-11-07
React router (carousel) | 2 | 5 | User | [6 empty] | x | 2018-11-30
SASS styling (pages) | 2 | 21
Style Causes & Effects page | 2 | 5 | User | [6 empty] | x | 2018-11-21
Build and style Resources page | 2 | 3 | User | [6 empty] | x | 2018-11-21
Image/icon processing and export | 2 | 3 | User | [6 empty] | x | 2018-11-19
Front page and Resources page | 2 | 5 | User | [6 empty] | x | 2018-11-28
Fix bugs (styling and responsiveness) | 1 | 5 | User |  |  |  |  | x